## phases
Phase_name | Phase_percent | Phase_percent_end | Notes (Phase) | Milestone | Due | Notes (Milestone)
Pre-Design | 0-10% | 0.1 | There is not a formal milestone or design review which signifies the completion of this phase; however, the milestones which are due in this phase will prevent further project work if they are not completed before 30% Design Approval. | Compatability Report (Draft) | 0.01 | This deliverbable is not defined in the Design Manual, contact your WSDOT repersentative for clarification. Draft version needs to be delivered at 1% Design Phase and is used to inform EIS and Alternatives Analysis.
Pre-Design | 0-10% | 0.1 | There is not a formal milestone or design review which signifies the completion of this phase; however, the milestones which are due in this phase will prevent further project work if they are not completed before 30% Design Approval. | Compatability Report (Final) | 0.05 | This deliverbable is not defined in the Design Manual, contact your WSDOT repersentative for clarification. Final version delivered at 5% Design Phase - this can be bumped to 10% depndeing on the project and agreement with WSDOT contacts.
Pre-Design | 0-10% | 0.1 | There is not a formal milestone or design review which signifies the completion of this phase; however, the milestones which are due in this phase will prevent further project work if they are not completed before 30% Design Approval. | Basis of Design | 0.05 | NA
Conceptual Design | 10-30% | 0.3 | This phase is formally completed with the acceptance of the Design Approval by WSDOT. | DESIGN APPROVAL | 0.3 | Design approval includes: a memo that describes the project, Project Summary Documents, Design Criteria, Design Variances, known deviations, applicable Channelization plans, Intersection plans, Interchange plans, or Alignment plans and a current cost estimate. See Design Manual Chapter 300
Final Design | 30-100% | 1 | This phase is formally completed with the acceptance of the Project Design Approval by WSDOT. | PROJECT DEVELOPMENT APPROVAL | 1 | Final approval of all project development documents by the designated representative of the approving organization prior to the advertisement of a capital transportation project. See Design Manual Chapter 300.\n \n <strong>NOTICE:</strong> Submittal of this document does not signify that construction can start, construction can only commence once this documnet has been approved - this process can last up to five months.
Construction Phase | 100+% | 2 |  | DDP DOCUMENTS | 1.5 | Items listed below must be completed before the PDA is signed and can be filed in the PDA or referenced in the PDA and filed with the DDP. There are other items that are required for advertisement that are contained in the Project File. A compilation of assumptions, decisions, justifications, and approvals that support the ultimate design of the project, to include review of the package. This file is designated for long term storage in accordance with WSDOT's document retention policies. See Design Manual Chapter 300. Basis Of Design, Scope Validation, Deliverables for the Project, Schedule, Cost Estimate, Risk management plan, Change management plan, Quality Management Plan, Human Resources Plan Project Profile - comprised of Project Definition, Environmental Review Summary, and Basis Of Design for a project.

## deliverables
DDP Checklist Items |  |  |  |  | Design Manual 300-2 Approvals
Milestone | Milestone_Percent | Deliverable | Design Manual | Notes | DM_approval_1 | DM_approval_2 | DM_approval_3 | DM_approval_4
Compatability Report (Draft) | 0.01 | Compatability Report (Draft) | NA | This deliverbable is not defined in the Design Manual, contact your WSDOT repersentative for clarification. Draft version needs to be delivered at 1% Design Phase and is used to inform EIS and Alternatives Analysis. | NA | NA | NA | NA
Compatability Report (Draft) | 0.05 | Compatability Report (Draft) | NA | This deliverbable is not defined in the Design Manual, contact your WSDOT repersentative for clarification. Final version delivered at 5% Design Phase - this can be bumped to 10% depndeing on the project and agreement with WSDOT contacts. | NA | NA | NA | NA
Basis of Design | 0.05 | Basis of Design | NA | NA | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Stamped Cover Sheet * | 300.04(1) | NA | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Design Approval Memorandum | 300.04(1) | Describing the Project | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Project Vicinity Map | PPM 400.06(4) | NA | Monumentation Map | NA | NA | NA
DESIGN APPROVAL | 0.3 | Project Summary Documents | 300.06(1) | Project Definition, Project Change Requests, Environmental Review Summary | Environmental Review Summary | NA | NA | NA
DESIGN APPROVAL | 0.3 | Basis of Design (BOD) * | 300.06(2), 1100.10(1) | NA | Basis of Design (BOD) | NA | NA | NA
DESIGN APPROVAL | 0.3 | Alternatives Comparison Table | 1104.03 | NA | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Design Parameter Sheets | 1100.10(4) | NA | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Safety Analysis or Crash Analysis Report | 321.04, 321.05 | NA | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Design Analysis | 300.06(4), 1106.07 | NA | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | List of Past Design Analyses (deviations) | 300.04(1) | Contact your ASDE for list | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | List of Past Maximum Extent Feasible (MEF) | 1510.5(2) | Contact your ASDE for list | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Interchange and/or Intersection Plans | 1360.07, 1310.07(2) | See region Channelization Plan Checklist | Intersection or Channelization Plans | NA | NA | NA
DESIGN APPROVAL | 0.3 | Alignment Plans and Profiles | 300.04(1), 1210.06, 1220.06 | If significantly modified | NA | NA | NA | NA
DESIGN APPROVAL | 0.3 | Basis of Estimate (BOE) with Cost Estimate | 300.06(3) | Compare to budget, No cost estimation (Doug Haight) | NA | NA | NA | NA
PROJECT DEVELOPMENT APPROVAL | 0.9 | Stamped Cover Sheet* | 300.04(2) | NA | NA | NA | NA | NA
PROJECT DEVELOPMENT APPROVAL | 0.9 | Project Development Approval Memorandum | 300.04(2) | Describing the Project | NA | NA | NA | NA
PROJECT DEVELOPMENT APPROVAL | 0.9 | Project Vicinity Map | PPM 400.06(4) | NA | NA | NA | NA | NA
PROJECT DEVELOPMENT APPROVAL | 0.9 | Any Design Approval items listed above that have been revised or added | 300.04(1) | NA | NA | NA | NA | NA
PROJECT DEVELOPMENT APPROVAL | 0.9 | NEPA Approvals | 300.02(1), 300.06(1)(b) | NA | Class l NEPA (EIS) | Class II NEPA – Categorical Exclusion (CE) Documented in ECS form | Class lll NEPA – Environmental Assessment (EA) | NA
PROJECT DEVELOPMENT APPROVAL | 0.9 | SEPA Approvals | 300.02(1), 300.06(1)(b) | NA | SEPA (EIS) | SEPA – Categorical Exemption (CE) | SEPA Environmental Checklist & Determination of Non-Significance (DNS) | NA
DDP DOCUMENTS | 0.6 | Maximum Extent Feasible (MEF) | 1510.05(1) | NA | ADA Maximum Extent Feasible Document (see Chapter 1510) | NA | NA | NA
DDP DOCUMENTS | 0.6 | Intersection Control Evaluation (ICE) | 321.05(2), 1300.05(1) | NA | Intersection Control Type | NA | NA | NA
DDP DOCUMENTS | 0.6 | Signals Permit | 1330.02(1) | NA | Signal Permits | NA | NA | NA
DDP DOCUMENTS | 0.6 | Median Crossover Approval | 1370.04 | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Traffic Analysis | 320 | NA | Crash Analysis Report | NA | NA | NA
DDP DOCUMENTS | 0.6 | Fencing | 560 | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Additional Illumination | 1040.05 | NA | Illumination Plans | Continuous Illumination – Main Line | Tunnel Illumination | High Mast Illumination
DDP DOCUMENTS | 0.6 | ITS Systems Engineering Documentation | 1050.05 | NA | Intelligent Transportation System (ITS) Plans | ITS Systems Engineering Analysis Worksheet (Exhibit 1050-2) | NA | NA
DDP DOCUMENTS | 0.6 | Roadside Clear Zone inventory | 1600.02 | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Barrier Length of Need Calculations | 1610.03(5) | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Public Art Plan | 950.05(1) | NA | Public Art Plan – Interstate (see Chapter 950) | Public Art Plan – Non-Interstate (see Chapter 950) | NA | NA
DDP DOCUMENTS | 0.6 | Bridge Vertical Clearance | 720.03(5)(c)(1), Exhibit 720-3 | NA | Bridge Design Plans (Bridge Layout) | Preliminary Bridge Plans for Unusual/Complex Bridges on the Interstate | NA | NA
DDP DOCUMENTS | 0.6 | Geological Reports | 610.04 | NA | Geotechnical Report | NA | NA | NA
DDP DOCUMENTS | 0.6 | Materials/Surface Reports | 610, 620 | NA | Pavement Determination Report | Resurfacing Report | NA | NA
DDP DOCUMENTS | 0.6 | Hydraulics Report | 800 & HM | NA | Signal Permits | NA | NA | NA
DDP DOCUMENTS | 0.6 | Railroad Crossing Evaluation Team Findings | 1330.045(7)(b), 1350.04 | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Railroad Grade Crossing Petitions and WUTC Orders | 1350.1 | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | MUTCD Request for Experimentation | 1330.07 | NA | Experimental Features | NA | NA | NA
DDP DOCUMENTS | 0.6 | Pedestrian Facilities | 1510 | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Value Engineering Recommendation Approval Form | 310.03(1) | NA | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Justifications/Design Decisions | Multi | Subjects range throughout the DM | NA | NA | NA | NA
DDP DOCUMENTS | 0.6 | Approvals | Multi | Exhibit 300-2, Subjects range throughout the DM | Work Order Authorization | NA | NA | NA
NA | NA | NA | NA | NA | Corridor Hearing Summary | NA | NA | NA
NA | NA | NA | NA | NA | Design Hearing Summary | NA | NA | NA
NA | NA | NA | NA | NA | Limited Access Hearing Plan | NA | NA | NA
NA | NA | NA | NA | NA | Limited Access Findings and Order | NA | NA | NA
NA | NA | NA | NA | NA | Final Project Definition | NA | NA | NA
NA | NA | NA | NA | NA | Interstate Access Revision Report | NA | NA | NA
NA | NA | NA | NA | NA | Any Break in Interstate Limited Access | NA | NA | NA
NA | NA | NA | NA | NA | Non-Interstate Access Revision Report | NA | NA | NA
NA | NA | NA | NA | NA | Break in Partial or Modified Limited Access | NA | NA | NA
NA | NA | NA | NA | NA | Right of Way Plans | NA | NA | NA
NA | NA | NA | NA | NA | Materials Source Report | NA | NA | NA
NA | NA | NA | NA | NA | Roundabout Geometric Design (see Chapter 1320 for guidance) | NA | NA | NA
NA | NA | NA | NA | NA | Tied Bids | NA | NA | NA
NA | NA | NA | NA | NA | Structures Requiring TS&Ls | NA | NA | NA
NA | NA | NA | NA | NA | Preliminary Signalization Plans | NA | NA | NA
NA | NA | NA | NA | NA | Signalization Plans | NA | NA | NA
NA | NA | NA | NA | NA | Rest Area Plans | NA | NA | NA
NA | NA | NA | NA | NA | Roadside Restoration Plans | NA | NA | NA
NA | NA | NA | NA | NA | Planting Plans | NA | NA | NA
NA | NA | NA | NA | NA | Grading Plans | NA | NA | NA
NA | NA | NA | NA | NA | Work Zone Transportation Management Plan/Traffic Control Plan | NA | NA | NA