## Table 1
deliverables expectations matrix_2020-june-16.docx
[9 empty] | planning, scoping/pre-design or design teams |  | typically design teams final design and preliminary contract documents engineering (ps&e) development | [8 empty] | transition to construction
This tool offers “at-a-glance” information about deliverables during design and project development. Check appropriate resources and subject matter experts for details regarding specific deliverables for your project. | [8 empty] | Planning corridor sketch strategies | Scoping/pre-design | Pre 30% |  |  |  | geometric design review (design approval) |  | constructability review | pre-contract review | Contract documents ready | Contract ad and award |  | Design Phase Closure
contents |  |  |  |  | consult or discuss with | [9 empty] | ~30% |  | ~60% | ~90% | 100%
1 | Timeline actions and purpose
2 | Project Management
3 | Cost Estimates
4 | Environmental Review, Permitting & Documentation
5 | Cost Risk Estimating Management
6 | Value Engineering
7 | Pavement
8 | Utilities and Railroad
9 | Access – limited/managed
10 | Right-Of-Way
11 | Community Engagement
12 | Design Documentation
13 | Roadway Geometrics and Plans
14 | Channelization and Pavement Marking Plans
15 | Hydraulics and Storm water
16 | Survey & Mapping
17 | Structures, Bridges, et al
18 | Illumination, signals and ITS
19 | Geotechnical Recommendations
20 | Work Zone Traffic Control
21 | Traffic Analysis
22 | Safety Analysis
23 | Signing
24 | Temporary Erosion and Sediment Control (TESC)
25 | Specifications
26 | Maintenance
LEGEND
Blue shading = a new row, added since the last deliverables expectations matrix
Orange shading = if applicable these groups/activities may be involved at these times in your project
Orange pattern = sometimes these activities are happening during this time frame
Law/ |  | Maintenance &
Legislature |  | Operations |  |  | Planning | Planning |  |  | Scoping |  | Programming | [5 empty] | Design |  | Construction
Page 1 of 11 | [13 empty] | deliverables expectations matrix_2020-june-16.docx
deliverables expectations matrix_2020-june-16.docx
Deliverables Expectation Matrix Communicates typical expectations for project deliverables and helps establish mutual understanding of these expectations. Provides a “schematic” of the Project Development Process at WSDOT - The matrix is foundational to seasoned project managers, project teams, staff and our consultant partners. The matrix offers additional value as a guide for staff learning how to complete a WSDOT project. This tool is used to help plan and execute work for project development. The matrix offers Quality Control, Quality Assurance and Quality Verification benefits. The matrix helps team readiness for project reviews and organizes the project development process as follows: Planning (corridor sketch strategies) Scoping Pre 30% Geometric design review / design approval (~ 30% design level) Constructability review (~60 design level) Pre-contract review (~90% design level) Contract documents ready (~100% design level) Contract ad and award Design Phase Close Out
Deliverables Expectation Matrix
Master Deliverable List (MDL)
Project Management Guide
project teams |  |  |  | new designers |  |  |  | subject matter experts | [7 empty] | traffic
consultants |  |  |  | design |  |  |  | design-builders | [7 empty] | specialty firms
Page 2 of 11 | [11 empty] | deliverables expectations matrix_2020-june-16.docx
|  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
1 | Timeline actions and purpose |  | project profile informs scoping and design start; begin Basis of Design with initial baseline project need |  |  |  | Identify team members  consultants, wsdot staff, or combination  core team members  extended team members  roles and responsibilities | [11 empty] | design criteria final design decisions design approval Design Manual Ch. 300 Basis of Design complete |  |  |  | major design elements completed underground & overhead conflicts identified resolve conflicts: utilities, | deliverables substantially complete document to reviewers | Region PS&E review (typically 10 weeks). | WSDOT publicly solicits bids from contractors to construct the project. | organized cessation of activities; transition work or staff Archive required records
[7 empty] | project endorsement | [15 empty] | drainage, etc.
[7 empty] | design criteria draft | [15 empty] | review constructability
[7 empty] | assumptions | [15 empty] | 3D modeling complete
deliverable requirements project delivery method
2 | Project Management |  | corridor level vision |  |  |  | PMP & work plan (DBE goals) Project Kickoff (initiate & align worksheet) Baseline schedule Budget known Risk Management Plan Communication plan Change management plan Quality Management Plan (QA, QC, QV) Endorsement Executing work | [11 empty] | Current project management plan (and work plan) – Design Manual 305; monitor & control (Quarterly Project Report), Capital Program Development & Management Office (CPDM) Manual Quality: Control – actions at the production levels to produce the desired quality and professional services. Assurance – actions to ensure prudent quality control procedures are in place. Verification – actions to ensure a Quality Management Plan (QMP) was implemented and followed. | [6 empty] | Official closure and handoff Lessons learned recognized accomplishments organized end of design activities transition of work or staff documentation per retention requirements
3 | Cost Estimates |  | Basis of Estimate Preliminary cost estimate developed for Project Definition |  |  |  | updated estimate & basis Budget assumptions communicated Determine if project needs: Value Engineering and/or Risk Assessment updated estimate & basis | [11 empty] | Begin item by item Project Estimate (update basis of estimate) R/W Project Funding Estimate completed |  |  |  | Estimate item quantities and unit costs. (update basis of estimate) updated estimate & basis Pay groups and pay items determined | Check that all items are included and correct. (update basis of estimate) Cost estimate completed with below the line items. Summary of quantities completed, item prices determined, | engineer’s estimate at ad Verify that all items are included and correct. (final basis of estimate) Construction estimate finalized
lump sum cost detail completed
4 | Environmental Review, Permitting, & Documentation |  | Identify and confirm level of required environmental documentation. | [15 empty] | Coordination with agencies NEPA/SEPA compliance documentation |  |  |  | Coordination with agencies NEPA/SEPA Compliance documentation Environmental Permit Applications | Coordination with agencies NEPA/SEPA compliance documentation | Coordination with agencies NEPA/SEPA Compliance documentation Environmental Permit Applications
|  |  | Environmental Review Summary completed. |  |  |  | Verify permits and documentation needed Environmental budget and schedule submittal Agreement on Area of Potential Affect for Section 106 and Action Area for ESA coordination with agencies
Environmental surveys of project footprint
Complete necessary Env docs and permits to complete Geotech work
|  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
5 | Cost Risk Estimating Management |  | Early determination of project needs for project risk assessment: Cost Risk Assessment, CRA or Cost Estimate Validation Process, CEVP. |  |  |  | Project Risk Assessment process steps are built into the project management plan, work schedule and scope of work. Review the Project Risk Management Guide; milestones for Scope, Schedule and Estimate are used to inform the timing of activities for project risk assessment. This includes updates. Establish milestones for cost risk assessment prep meetings and activities, workshop(s) and post workshop activities in the project schedule. Schedule Risk monitoring and control activities. | [11 empty] | Status of project risks. Update analysis if needed. |  |  |  | Status of project risks. Update analysis if needed. | Status of project risks. Update analysis if needed. | Prepare summary of project risk status. |  | Transfer summary of project risk status to construction office.
6 | Value Engineering |  | Early determination of benefit of Value Engineering for the project. |  |  |  | Review the Value Engineering chapter of the Design Manual. Value Engineering is an effective process for ensuring Practical Design. Value Engineering activities are built into the project schedule. | [11 empty] | Value Engineering workshop. |  |  |  | Implementation of Value Engineering recommendations. | Follow-up and follow- through of value engineering recommendations. | Prepare summary of value engineering recommendations as implemented into the final design.
7 | Pavement |  | Scoping Level Pavement Design Report completed, including: o WSPMS/Historical Data/Maintenance Input o Projected Traffic Type/Usage o Existing Conditions/Primary Deterioration o Highway Activity Tracking System, HATS o P1 One-Touch Policy |  |  |  | Scoping Level Pavement Design reviewed Region materials Pavement Design Report requested Preliminary Pavement Type Selection Completed Field and Core Investigation completed Draft Pavement Design Report completed | [11 empty] | Draft Pavement Type Selection completed Draft Pavement Design Report approved by Region, (sent to Pavement Office for concurrence) |  |  |  | Pavement Type Selection submitted to Pavement Office for Final Approval Draft Pavement Design Report completed Final Pavement Design Document stamped by Region and forwarded to Pavement Office for signed concurrence | Final Pavement Design Report with Region stamp and Pavement Office signed concurrence to Region for Plan Review |  | Pavement Repair quantities and locations reviewed with Construction PEO for verification of field accuracy
|  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
8 | Utilities and Railroad |  | Potential utility relocations identified Responsibility for costs established |  |  |  | Utilities within the project limits notified. Washington Utilities Transportation Commission (WUTC) permit application for railroad crossings submitted Utility As-Builts requested. Railroad (RR) issues identified. Relocation cost responsibility defined. Franchise and permit documentation collected. | [11 empty] | Utility Conflict Report & Plan with as-built info. Preliminary Utility conflicts identified. Utility Object Relocation Record-UORR sent to Utilities. Project Overview Meet w/Utility Owners Utility Quality Level C & D completed. |  |  |  | Utility conflicts confirmed and relocation letters sent to Utilities. Utility relocation meeting held. Utility Relocation Plans and schedules obtained. Utility and railroad agreements completed | Utility Relocation Plan information and specifications incorporated in PS&E. Letters of Understanding issued to Utilities requiring relocation. Utility, service, and railroad agreements completed. |  | Utility relocation work completed or timeline established
[7 empty] | Utility relocation strategy for project established. | [11 empty] | Determine need for Subsurface Utility Engineering, SUE Utility Quality Level A& B. |  |  |  | Utility Franchise/Permit obtained. | Utility relocation and schedule monitored and coordination completed.
[19 empty] | Relocation plans/schedule request from Utilities. Franchise/Permit process initiated; cost recovery accounts initiated. |  |  |  | Finalize utility agreements (costs responsibility estimate complete) | Construction and Maintenance Agreement completed.
Utility property rights verified.
Railroad standard Construction Maintenance Agreement (CMA) obtained
9 | Access – limited/managed |  | Define existing access status; managed access and/or limited access |  |  |  | Limited access | Identify affected abutters for access report and hearings. | [10 empty] | Access Hearing Plan and hearing process |  |  |  | New Limited Right of Way Limited Access Plan
| DM 520, 530, 540, 550, 1103 DM 210 (hearings) |  | A choice to change current or planned access is to be consistent with the contextual information, desired performance targets, and modal priorities. DM 1103. Evaluate Access Master plan - determine most appropriate access control. Document in BOD Section 3. |  |  |  |  | Determine if an access hearing is required. Evaluate access connections and identify improvements. Limited Access Change Access hearing required or notice of opportunity for a hearing. Access hearing Access Report and Access Report Plan prehearing packet | [10 empty] | Findings and Order Plan Appeal Period Resume
Identify general project impacts to access.
[7 empty] | Managed Access | Review grandfathered approaches and existing permitted approaches. Evaluate access connections and identify improvements. Is it appropriate to combine or close connections and reduce traffic conflicts? | [10 empty] | Managed Access Control Permits in the RAMPS database, reviewed and updated. RAMPS = Roadway Access Management Permit System |  |  |  | Note: Managed Access connections are not noted on the Right-Of- Way plans. There is no Right-Of-Way plan change unless WSDOT requires Right-Of-Way.
|  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
10 | Right-Of-Way Right of Way Manual, Chapter 6 |  | Property required for a public facility, includes square footage, access rights, easements, and any property impacts. |  |  |  | Real Estate Services assists in minimizing right of way costs, defining route locations and acquisition areas, and determining potential problems and possible solutions. | [11 empty] | Plan development: “red line R/W plan” R/W cost estimates made by Real Estate Services. |  |  |  | Confirm status of right of way acquisition. • Examine Title reports. • Add easements to right of way and limited access plan. • Obtain utility, railroad, haul road, detour routes, or other essential agreements. Utilities Manual and the Agreements Manual. • Plan right of way acquisition, disposal, and maintenance. • Plan easements and obtain permits (to accommodate activities outside of the right of way). | Right-of-way acquisitions complete.
| Design Manual 510 | [5 empty] | Appraisals and Acquisition information
|  |  | Consider significant right of way elements in accordance with the Right of Way Manual. | [15 empty] | Request title reports for identified right of way parcels.
Real Estate Services performs field inspections as appropriate.
11 | Community Engagement |  | multimodal, multiagency, multidisciplinary engagement concept team launch create stakeholders list get input from region communications |  |  |  | community engagement plan complete confirm need & context Design controls Alternatives Analysis preferred alternative Elements/Dimensions Identified Dimensioned | [11 empty] | Investigate design concepts that Incorporate community feedback |  |  |  | Investigate design concepts that Incorporate community feedback | Community engagement ideas fully implemented into contract plans
12 | Design Documentation |  | Context Management Assessment Report (CMAR) complete BOD initiated |  |  |  | Section 1 and 2 of the BOD complete. Baseline and contextual needs including performance metrics and targets. Context determined. Section 3 and 4 in draft form circulated for concurrence. | [11 empty] | All sections of BOD complete and BOD approved |  |  |  | If a separate Design Approval is necessary, it should be completed in this phase. Design Analysis completed. | Project Development Approval complete or combined Design Approval/Project Development Approval complete. | Design Documentation Package complete |  | Design documentation transferred to construction project office.
13 | Roadway Geometrics and Plans |  | Project limits identified Affected alignments identified | [9 empty] | Design criteria and parameters approved Preliminary footprint designed | [5 empty] | Typical roadway section(s) completed; station to station roadway geometrics, surfacing type & depth, slope information, guardrail, vertical cut locations, and construction notes Mainline and major horizontal, & vertical alignments, and superelevations designed |  |  |  | All horizontal & vertical alignments & superelevations completed | All geometric plans completed (alignment, profiles, roadway sections, interchange contours, site preparation, road approach plans, etc.) Design compared to endorsed design criteria/ parameters | Final Plans for PS&E contract
New versus existing alignment
Design Analysis approved
Target speed
DDP updated as required
Preliminary design criteria established
Project Development > |  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
14 | Channelization and Pavement Marking Plans | [5 empty] | Intersection Control Analysis (ICA) approved (if not already complete in scoping) | [11 empty] | Roundabout Geometric Design Peer Review complete. Intersection Plans for Approval submitted for review. |  |  |  | Design Analysis submitted and approved Intersection plans for approval complete | All plans completed Approved Channelization Plan verified for consistency with pavement marking plans and specifications
Signal permits completed.
Striping material selected.
15 | Hydraulics & Storm water see Temporary Erosion and Sediment Control (TESC) |  | Drainage needs identified in accordance with Maintenance and Regional Hydraulics |  |  |  | Stormwater Management requirements identified Design criteria identified Water quality requirements identified Stormwater Retrofit Cost-Effectiveness and Feasibility (RCEF) Phase I Analysis complete Confirm specific criteria for: - Fish Passage - Chronic Env Deficiency - Major Drainage - Bridge Scour/ replacement | [11 empty] | Stormwater Management strategies, including locations for treatment and/or flow control, identified (to meet hydraulic and stormwater requirements) Sensitive Area Documentation completed (Water |  |  |  | 60% check-in / Hydraulic Report Checklist TS&L of drainage facilities determined draft Hydraulic Report, - Document needs - Existing basins & flows for anticipated Threshold Discharge Areas - Identify Minimum -- Requirements from | Hydraulic Report Final approved verified for consistency with plans and specifications Stormwater details completed As a result of previous Stormwater RCEF analysis, if applicable, transfer stormwater
[19 empty] | Resource Inventory). |  |  |  | Highway Runoff Manual | retrofit funds to the I-4
[19 empty] | Stormwater |  |  |  | (HRM). | Subprogram, Stormwater
[19 empty] | Management Strategy |  |  |  | Hydraulics Report | Retrofit Category
[19 empty] | endorsed by region or |  |  |  | submitted to region for
[19 empty] | HQ hydraulics engineer |  |  |  | review and approval | Final Hydraulic Design,
[23 empty] | Hydraulic Report | i.e. stream design
Submitted
Preliminary Stormwater
Mgmnt options to
identify R/W needs
completed
Preliminary Hydraulics
Design, i.e. stream design
Stormwater RCEF Phase
II Analysis complete
16 | Survey & Mapping |  | LIDAR or existing aerial photos or other preliminary information. |  |  |  | Project survey requirements finalized, including areas that may be outside roadway corridor improvements. Project survey control completed Cadastral survey performed. Topographic Survey complete. | [11 empty] | Design level mapping completed Record of Survey completed and filed Right of Way plan completed and approved Relocation plan completed |  |  |  | Mapping of new roadway features completed Field review of proposed features completed | DNR Permits to Destroy Monuments obtained | Preliminary construction staking data completed
Project Development > |  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
17 | Structures (Bridges, Retaining Walls, Noise Walls, high mast lighting, sign structures) Also, refer to “Structural Submittal Expectations Matrix”. |  | Determine needed |  |  |  | Structural Input for | [5 empty] | Structural Participation in | [5 empty] | Refer to Deliverables in the Structural Matrix “Bridge Preliminary Plan” Required Information from Others:  Structure Site Data  Preliminary Hydraulic Design (PHD)  Geotechnical Information for Bridge Preliminary Plan Submittal: Draft Bridge Preliminary Plan End of Phase Document: Approved Bridge Preliminary Plan |  |  |  | Refer to Deliverables in the Structural Matrix “Constructability Review Set” Required Information from Others (4 weeks prior to submittal):  Geotechnical Information for Bridge Substructure Design  Draft Bridge Scour Recommendations Submittal: Constructability Review Set End of Phase Document: Finalized Comment Resolution Form | Refer to Deliverables in the Structural Matrix “PS&E Review Set” Required Information from Others (6 weeks prior to submittal):  Final Geotechnical Recommendations  Final Hydraulics Design (FHD) Submittal = End of Phase Document: PS&E Review Set | Refer to Deliverables in
|  |  | structure and/or geotech work. |  |  |  | Environmental Documentation and | [5 empty] | Agency Coordination | [11 empty] | the Structural Matrix “Signed PS&E Set”
[7 empty] | Permits | [5 empty] | Finalize Scope of Work
|  |  | Square footage cost | [9 empty] | Agreements
|  |  | estimates of structures |  |  |  | Begin Coordination:
project scope,
preservation activities,
construction staging,
layout and span lengths,
design constraints,
seismic operational
classification
[7 empty] | Submittal: TS&L (when | [17 empty] | Submittal: Signed PS&E |  | Submittal = End of Phase:
[7 empty] | required) | [17 empty] | Set (2 weeks prior to End |  | Bridge Load Rating
of Phase)
18 | Illumination, Signals and ITS |  | Establish required light levels (roadway and pedestrian classification). Determine ITS needs and preliminary equipment locations. |  |  |  | Coordinate with signal operations for any proposed new or modified traffic signal systems. Signal operations will develop signal-phasing plan(s) as part of signal system analysis. Start speed study for existing intersections. Begin collection of as-built data for existing locations. | [11 empty] | As-built information collected and verified on- site with maintenance. |  |  |  | Box/vault, cabinet, and conduit layout complete. Wiring / network (fiber) diagram complete. Signal display and detection laid out and identified. Provide data to Bridge and Structures Office for any special design equipment or foundations. | All notes and schedules complete, including review and approval of supporting calculations. Supporting detail plans complete. Provide service agreement requests (power or communications) to utilities office for processing. | Final plans complete. Service agreements complete.
[19 empty] | Illumination |  | Light Level
Analysis complete.
Signal phasing plan complete. Preliminary signal plan approved.
Pole locations provided to design for coordination of grading and drainage Confirm lateral bearing pressure design for poles Wind load charts for signal standards Contact structural designer for poles mounted on structures.
Determine preliminary utility connections (power or communications) and initiate coordination with serving utilities.
Project Development > |  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
19 | Geotechnical Recommendations |  | Scoping level cost estimate for project/workforce planning, based on project size, location, known elements & historical costs. |  |  |  | Support for TS&L Submittal: TS&L (when required) | [5 empty] | Required Information from Others:  PMP  Work Request  Scope of Work Agreement  Draft Schedule Submittal: Cost estimate provided, based on project size, location, known elements & historical costs. End of Phase Document:  PMP endorsement  Scope of Work agreements initiated  Draft Schedule | [5 empty] | Required Information from Others:  Project Site Data; o Mainline and major horizontal & vertical alignments o Typical roadway section(s) o TS&L of all Structures o Wall Site Data o Hydraulic/Storm water features  Field Exploration Clearances, ROE and cultural resources.  Preliminary Hydraulic Design (PHD) Submittal:  Geotechnical Information for Bridge Preliminary Plan  Drilling Exhibit for ESA End of Phase Document:  Final SOW Agreement  Final Cost estimate & Schedule |  |  |  | Required Information from Others:  Approved Bridge Preliminary Plan  Roadway sections  Draft Bridge Scour Recommendations  Survey Borehole locations Submittal:  Field Exploration Plan & utility locates  Soils Data to Hydraulics  Geotechnical Information for Bridge Sub-Structure Design | Required Information from Others:  Final Hydraulic Design (FHD) End of Phase Document:  Final Geotechnical Recommendations (Report/Memorandum) | Required Information from Others:  PS&E Review Set Submittal:  PS&E review comments End of Phase Document:  Summary of Geotechnical Conditions | End of Phase Document:  Decommissioning of wells | Project close out & transition to Construction support
20 | Work Zone Traffic Control |  | Basic traffic control strategies & alternatives identified. Projects of significance must have Traffic Management Plan (TMP) scoped. | [15 empty] | Preliminary Traffic Management Plan/Traffic Control Plan |  |  |  | TMP showing construction sequence and staging completed | Final TMP completed. Final detour plans completed | TMP, including traffic control plans completed and associated Specials approved
21 | Traffic Analysis |  |  Scoping level operational analysis complete for alternatives consideration |  |  |  |  Operations analysis scope determined  Traffic data collected  Perform Operations Analysis  Intersection Control Evaluation (ICE) approved (if not already complete in scoping) | [11 empty] | Operations analysis complete. ARR complete (note: the ARR was previously known as the Interchange Justification Report, IJR). |  |  |  | Assumptions and conclusions in Operations Analysis verified for consistency with design.
Operations Analysis
Access Revision Report
(ARR)
22 | Safety Analysis Crash Analysis Report (CAR) |  | Reference Safety Analysis Guide for what will be needed for safety analysis for the funding program. |  |  |  | Gather data necessary for Safety Analysis. Perform Safety Analysis | [11 empty] | Safety Analysis complete. |  |  |  | Assumptions and conclusions in Safety Analysis verified for consistency with design.
CAR is complete if funded from the Collision Reduction program.
Project Development > |  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
23 | Signing | [5 empty] |  Contact Region Traffic Office to discuss scheduling, scope of project, and needed information for sign design  Gather and deliver signing information to the Traffic Office | [11 empty] |  Existing signs to reuse and relocate defined  Existing sign inventory complete(include electrical items for sign lighting, flashing beacons, or variable/dynamic message signs)  Potential conflicts between light standards, camera poles, and signal poles with signs identified  Requests for sign structures submitted to HQ Bridge and Structures  Preliminary Guide Sign Plan developed  Preliminary Lump Sum Estimate calculated |  |  |  |  Visual standards for corridor coordinated with Landscape Architect  Signing plans, notes, sign specifications completed  Conflicts with illumination, camera poles, and/or signal features, drainage or utilities identified  Coordination with luminaires on structures or walls identified and mounting/foundation details completed  Updated Lump Sum Estimate  Utility Agreement and Utility Relocation Requests submitted  Sign layout complete, include overhead signs |  Updated Sign Design Plan Sheets (Sign Specification Sheets – Removal, Relocation, & Roadside Sign Structures; Sign Plans; Sign Details)  Overhead Sign Structure Plan Sheets completed  Update Lump Sum Estimate
24 | Temporary Erosion and Sediment Control (TESC) |  | Extent of anticipated ground disturbance identified Need for environmental permits identified (including but not limited to NPDES) Preliminary identification of specific site conditions (sensitive areas, contamination, etc) and potential environmental commitments |  |  |  | Type of TESC plan identified – full TESC Plan vs. Abbreviated TESC Plan/TESC Memo Project timing/duration determined | [11 empty] | Locations of disturbance and BMPs identified for TESC Planning Preliminary Grading Plans developed Streams/water bodies and other sensitive areas finalized for Construction Stormwater General Permit (CSWGP) Notice of Intent (NOI) and TESC planning |  |  |  | Preliminary TESC Plan developed and reviewed by Region Environmental & Construction Cut and fill lines identified Clearing limits identified | Preliminary TESC Plan finalized and accepted Bid items, Special provisions identified CSWGP NOI submitted | Preliminary TESC Plan, partially completed Transfer of Coverage (TOC) forms, and CSWGP added to contract and sent to Contract Ad & Award | Contractor signs TOC and sends back to WSDOT WSDOT State Construction Engineer signs TOC form Contract Administration and Payments Section (CAPS) adds “Specific Date of Transfer” and mails final TOC form to Ecology Contractor either accepts TESC Plan (and modifies) or develops their own | Temporary Erosion and Sediment Control (TESC)
|  |  | Environmental Review Summary (ERS) developed and submitted to Region Environmental for review and comment | [22 empty] | Contractor develops S Spill Prevention, Control, and Countermeasure (SPCC) Plan as a Type 2 working drawing and submits to WSDOT for review/acceptance
Project Development > |  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
25 | Specifications | [17 empty] | Start writing specials for non-standard bid items. |  |  |  | Specifications preliminary run list completed | Specifications run list completed All special provisions submitted for review and approval. Specialty groups specifications and special provisions completed Pay groups and pay items determined | Approved Specifications included in PS&E
Project Development > |  |  | Scoping/pre-design |  |  |  | project management plan development | [11 empty] | geometric design review |  |  |  | constructability review | pre-contract review | contract ready (final review) | Contract Ad and Award | Design phase Closure
|  |  | corridor sketch / planning study |  |  |  | ~10% | [11 empty] | ~30% |  |  |  | ~60% | ~90% | 100% | bid letting | Transition to construction
26 | Maintenance |  | Include nearest Maintenance Operations Area to ensure initial planning optimizes maintainability to maximize life cycle costs of all features for maintenance operations after project completion. Meet to discuss current  Pavement  Utilities  Right-Of- Way  Hydraulics  Structures  Drainage  Safety Identify how the planning may affect existing assets. Establish whether the scoping will have budgetary impacts to the Maintenance Operations forces after project completion. |  |  |  | Ensure initial planning takes into account maintainability, life cycle costs, and accessibility for maintenance operations after project completion. Meet to discuss current issues with:  Pavement  Utilities  Right-Of- Way  Hydraulics and Storm water  Structures  Drainage  Safety Ensure that the environmental impacts to Maintenance concerns have been documented and are part of the completed Environmental Review Summary. | [11 empty] | Verify guardrail design type takes into account:  maintainability  material costs and accessibility  limit exposure for traffic control |  |  |  | Review previously discussed maintenance and operations (M&O) items:  Pavement  Utilities,  Right-Of-Way Hydraulics  Roadway Geometrics  Plans  Structures  Drainage  Safety items | Allow Maintenance the opportunity to review the PS&E Package for maintainability to maximize the life cycle of all highway features within the project. | Ensure plan sets are received by all Maintenance offices involved in the process. |  |  Include asset owner’s manuals and notes needed for as-builds. Maintenance needs to receive any changes that occurred during design/construction for asset management purposes.
Establish
Policy Framework
Manage
System Assets
Identify
Needs
Assess
Alternative Strategies
Refine
Solutions
Assign
Resources
Develop
Funded Solutions
Implement
Solutions
Target Audience for the Deliverables Expectations Matrix includes…